## Sheet1
Week | Discussions | Agreements | Activities | Achieved
Week 1 | Discuss the project plan | Build the HR desktop app first | Assign roles and design wireframes | Create logo/UML and ERD diagram - Project plan
Week 2 | Discuss the user requirements specifications and the design concepts | Work on a URS document and design the wireframes for the application | Come up with additional features to add to the URS | GUI/Wireframes - User Requirements Specification document
Week 3 | Discuss the wireframes of the application and the URS | Update the URS and the wireframes and create a list of tasks to work on | Use the URS to start building the application | Update User Requirements Specifications document and start implementation
Week 4 | Give a demonstration | To build the must have requirements first | Assign tasks to the developers | Have basic working functionalities based on the hard-core functional requirements
Week 5 | Discuss a test plan and how to conduct the testing of the application | Have the application ready for the test phase | Test the application and create a test report | Test case, test report documents and application ready for delivery
Week 6 | What needs to be fixed and added in the application's next update | Fixed the bugs and update the application based on feedback/new features received from the client | Update then test the application and start working on the web application for the stock management | Deliver and deploy an updated version of the HR application
Week 7 | Reflect on the past six weeks and how to move forward. | Came up with some additional features that were set for Sprint 1. These features are for the web dev. | Assign tasks to the developers and work on the bugs for the HR app | Fixed bugs for the HR app and started working on the stock app
Week 8 | Sprint iteration, the features on git and bugs that were occurring and we talked about the design for the app | Agreed on the must have and should have features for the stock app. | Gave a short demo of the app in its current state and worked on the fetaures for the next sprint | All of the features for sprint iteration and fixed some bugs.
Week 9 | Sprint iteration and the features on git | We agreed that some features needed to be changed/updated to make the app more professional | Gave a demo of the app and worked on the featuresfor the next sprint | All of the features for sprint iteration and fixed some bugs.
Week 10 | Team discussed the progress of the project, features that can be changed for better understanding and how to make to finish the app in time | To come up with new features, if possible | Worked on the app and did a lot of testing | Finished the features for the following sprint iteration
Week 11 | Came up with some new features and discussed the design and some functionalities to make the app more user-friendly | We agreed on the features for the iteration. Also, we came up with new and agreed on the features for the next sprint iteration | Gave a demo of the app and worked on the featuresfor the next sprint | Testing and the features for the this week's sprint
Week 12 | Discussed some bugs and features in the stock app | Agreed to work on the bugs and update required documents for the release | Gave a demo of the app for the last sprint iteration for the stock app and we tested the app during this week | Did some heavy testing on the stock app and fixed some bugs before the release
Week 13 | Talk about the previous presentation | Prepare the project for code refactoring | Refactor the code in the project | Made some progress on the code refactoring
Week 14 | Sprint iteration with new features | Continue refactoring and work on the new features | Work on new features and refactor the code in the project | Made significant progress on the new features and refactoring
Week 15 | Sprint iteration | Continue refactoring and work on the new features | Testing and fixing bugs and work on new features | Made significant progress on the new features and refactoring
Week 16 | Sprint iteration | Start testing the project and fix bugs | Testing and fixing bugs | Give a preview of the application in its current state.
Week 17 | Last sprint iteration | Prepare for the final presentation and release | Testing and fixing bugs | Give a preview of the application in its current state.
Week 18 | Final Presentation | Project ready to deploy | Tested with the client | Deliver the project on time without issues